## Sheet1
NAME | DURATION | START | FINISH | TASK DONE BY
Mandate definition and planning | 2 hour | 2021-02-01 | 2021-02-02 | Jugraj singh
Data collection | 15 minutes | 2021-02-01 | 2021-02-02 | Jugraj singh
Research | 10 minutes | 2021-02-01 | 2021-02-02 | Jugraj singh
Theoretical solution | 20 minutes | 2021-02-01 | 2021-02-02 | Jugraj singh
Architecture design | 12 minutes | 2021-02-01 | 2021-02-02 | Jugraj singh
Production | 25 minutes | 2021-02-01 | 2021-02-02 | Jugraj singh
Client Presentation | 40 minutes | 2021-02-01 | 2021-02-02 | Jugraj singh
Visual Design | 6 Hours | 2021-02-02 | 2021-02-03 | Karan sehgal
Research | 45 minutes | 2021-02-02 | 2021-02-03 | Karan sehgal
Ideation | 27 minutes | 2021-02-02 | 2021-02-03 | Karan sehgal
Conceptualisation | 35minutes | 2021-02-02 | 2021-02-03 | Karan sehgal
Mock-ups | 1 hour | 2021-02-02 | 2021-02-03 | Karan sehgal
Client Presentation = Approval | 50 minutes | 2021-02-02 | 2021-02-03 | Karan sehgal
Alpha Version | 4 hour | 2021-04-02 | 2021-05-02 | Jugraj singh
Interface Segmentatiin | 25 minutes | 2021-04-02 | 2021-05-02 | Jugraj singh
Interface Integration | 20 minutes | 2021-04-02 | 2021-05-02 | Jugraj singh
Navigation Integration | 13 minutes | 2021-04-02 | 2021-05-02 | Jugraj singh
Testing and Corrections | 45 minutes | 2021-04-02 | 2021-05-02 | Jugraj singh
Beta Version | 3 hours | 2021-05-02 | 2021-05-02 | Karan sehgal
Image Creation | 45 minutes | 2021-05-02 | 2021-05-02 | Karan sehgal
Titles | 11 minutes | 2021-05-02 | 2021-05-02 | Karan sehgal
Texts and Images | 46 minutes | 2021-05-02 | 2021-05-02 | Karan sehgal
Programs Integration | 15 minutes | 2021-05-02 | 2021-05-02 | Karan sehgal
Testing and Corrections | 55 minutes | 2021-05-02 | 2021-05-02 | Karan sehgal
Client Presentation | 25 minutes | 2021-05-02 | 2021-05-02 | Karan sehgal
Implanation | 7 hors | 2021-06-02 | 2021-08-02 | Jugraj singh
Finalize SEO | 2 hour | 2021-06-02 | 2021-08-02 | Jugraj singh
Final Corrections | 1 hour 20 minutes | 2021-06-02 | 2021-08-02 | Jugraj singh
Online tests | 3 hours | 2021-06-02 | 2021-08-02 | Karan sehgal
Corrections/Adjustments | 2 hour | 2021-06-02 | 2021-08-02 | Karan sehgal